## CODi Issues Tracker
S.No | Issue / Discussion Point | Description | Expected Behaviour | Current Status | Solution / Resolution
1 | Deleted repo files still validated | Earlier, when a file was deleted in PR/repo, CODi attempted to parse it and threw errors. Also validated delete → re-add scenario. | Deleted files must be skipped gracefully; re-added files should validate normally. | ✅ Tested & Working | Added logic to detect and skip deleted files during PR validation. Re-added files are treated as new and validated normally.
2 | Python JDBC rules initially written only for process-level tags | Rules were checking <jdbcActivity> (process-level), while shared JDBC resources use different XML structure. | Rules must align with correct BW5 XML structure for shared resources. | ✅ Tested & Working | Updated Python JDBC rules to check both <jdbcActivity> (process-level) and the correct shared resource XML structure.
3 | Root tag / item tag missing cases | Internal review found failures when XML structure was incomplete (missing root/item tags). Now returns "No configuration found". | Proper structured error when configuration/tag missing. | ✅ Tested & Working | Added structured error handling to return specific "No configuration found for [config name]" messages instead of generic failures.
4 | .gv incorrectly treated as supported BW5 file type | .gv is not valid BW5 suffix; correct GV file is .substvar. | Only valid BW5 suffixes allowed; GV rule should apply to .substvar. | ✅ Tested & Working | Corrected file type mapping — removed .gv as a valid suffix and mapped GV rules to .substvar files only.
5 | .process files triggering JDBC shared rules | Concern that .process files may trigger JDBC shared rules unexpectedly. | Validation should follow BW5 suffix logic; .process ignored until dedicated rules added. | ✅ Tested & Working | Enforced BW5 suffix-based validation routing — .process files are excluded from JDBC shared rules until dedicated rules are added.
6 | Merge blocking vs warning-based reporting | Concern that CODi blocks merge completely when validation errors exist. Clarified override must be allowed. | Show validation errors but allow authorized reviewer to merge. | ✅ Tested & Working | Validation errors are shown as warnings; merge is blocked only on hard GitHub restrictions (merge conflicts). Authorized reviewers can override.
7 | Only 4 rules currently implemented (Scope confirmation) | Current engine includes: JDBC Username, JDBC Password, JDBC Timeout, GV Description. | Within current agreed scope, this is acceptable. | ✅ Tested & Working | Confirmed scope — 4 rules (JDBC Username, JDBC Password, JDBC Timeout, GV Description) are within the agreed implementation boundary.
8 | Unsupported files incorrectly parsed | Bot earlier attempted to parse unsupported files (.txt, .html, .js, .xml, .md, .log). | Unsupported files must be ignored silently. | ✅ Tested & Working | Added an explicit allowlist of supported BW5 file types; all other file types are silently skipped.
9 | Nested folder, mixed structure & multi-PR/webhook validation | Earlier inconsistency with nested folders. Also need to validate: Same repo – 2 PRs modifying same file • Multiple repos – parallel PRs • Webhook triggering across repos. | Validation must work reliably across nested folders and concurrent PR events across repos. | ✅ Tested & Working | Fixed folder traversal logic to handle nested structures. Validated concurrent webhook triggers across multiple repos and PRs.
10 | Variable-related messages too technical | Validation error messages exposed internal variable names and technical implementation details not relevant to end users. | Error messages should be simplified and user-friendly, avoiding internal variable names or code-level references. | ✅ Fixed | Replaced technical variable names in error messages with plain-language descriptions understandable by non-developers.
11 | Local file paths used instead of repo-relative paths | Error messages and file references displayed full local paths (e.g., C:\...) instead of repository-relative paths. | All file path references should use repo-relative format (repo/branch/filename) instead of local machine paths. | ✅ Fixed | Updated path references to use repo-relative format: repo/branch/filename instead of full local machine paths (e.g., C:\...).
12 | Folder path separator inconsistency | Folder paths in validation output used inconsistent separators (mix of forward slashes and backslashes), causing display and parsing issues. | All folder paths must use a standardized separator consistently throughout the application. | ✅ Fixed | Standardizing all folder path separators to use forward slashes (/) consistently throughout validation output and messages.
13 | Enterprise Git version not documented | Documentation covers only the Free version of GitHub. Enterprise Git has different configurations, endpoints, and settings that are not yet documented. | Documentation should be created for the Enterprise version of Git, covering setup, configurations, and any behavioural differences from the Free version. | 🔄 In Progress | Documentation for Enterprise Git version to be created, covering setup, endpoints, webhook configuration, and differences from the Free version.
14 | Time lag in loading CODi validations | The old code called get_fix_suggestion(use_ai=True) inside the file loop — one file at a time, sequentially. The slowness was purely in get_fix_suggestion() being called one by one. | Validation results for all files should be collected first, then AI fix suggestions fetched simultaneously using ThreadPoolExecutor for parallel processing. | ✅ Fixed | Refactored code to collect all validation results across all files first, then fetch AI fix suggestions in parallel using ThreadPoolExecutor — eliminating sequential one-by-one AI calls.
15 | Extended description auto-populated in commit/merge window | An "Extended Description" section appeared in the commit/merge window. This is automatically generated by GitHub during Squash and Merge, listing all individual commit messages from the PR branch as bullet points. | The extended description field generated by GitHub's Squash and Merge should be reviewed and removed or suppressed from the merge window UI. | ✅ Clarified — Expected GitHub Behaviour | Clarified this is standard GitHub behaviour during Squash and Merge — the extended description is auto-generated by GitHub and lists individual commit messages.
16 | Rule name used as error string in validation output | Validation errors were displaying the internal rule name (e.g., JDBC_USERNAME_CHECK) as the error message shown to users. | Error messages displayed to users must be descriptive, human-readable strings — not internal rule identifiers. | ✅ Fixed | Changed error output to use human-readable descriptive messages instead of internal rule identifier names (e.g., JDBC_USERNAME_CHECK).
17 | Validation errors not sorted per file name | Validation error output was not organized by file, making it difficult to identify which errors belong to which file. | Validation errors should be grouped and sorted alphabetically by file name for clarity. | ✅ Fixed | Updated validation output to group and sort errors alphabetically by file name for easier review.
18 | Missing configuration shows generic "No configuration found" message | When a required configuration was missing, the error message only said "No configuration found" without specifying which configuration was missing. | The error message should clearly identify which specific configuration is missing (e.g., "No configuration found for JDBC Shared Resource"). | ✅ Fixed | Updated error messages to explicitly state which configuration is missing (e.g., "No configuration found for JDBC Shared Resource: db-connection.sharedjdbc").